## Naming Rules (hidden)
- No decimals or periods used in titles
- Descriptions have the full name (no acronyms or truncated words)
- Where there is no formula, formula will show the data source |  | Decisions
- Within the IS column name operators do NOT have spaces around them
Question for John
| In CBS - when it says Const. Equip. total cost, is it referring to C E or Budget? |  | C E

## CBS
Column Name | Short description | Additional column information | Formula (for terminals and items where Allow as-built <> None)
% complete | Percent complete | The denominator depends on what was selected in Project settings (either Forecast (T/O) qty or CB total qty) | [Actual qty (to date)] ÷ [Forecast (T/O) qty]
Account code |  | More details of account codes can be found in the ACS.
Account code description |  | Description of the associated account code. More details of account codes can be found in the ACS.
Actual allowance cost (to date) | Actual contingency (allowances) cost (to date)
Actual construction equipment cost (to date)
Actual cost (to date) | Actual cost claimed (to date) | IF Estimated actual cost is ON, THEN [Confirmed actual cost] + [Estimated actual cost]
Actual eqp hrs (to date) | Actual equipment hours claimed (to date) | IF Estimated actual cost is ON, THEN [Confirmed actual equipment hours] + [Estimated actual equipment hours]
Actual fees cost (to date) | Actual fixed fees and services cost (to date)
Actual finish
Actual FOM rented equipment cost (to date) | Actual field operated and maintained rented equipment cost (to date)
Actual G & A cost (to date) | Actual general and administrative expense cost (to date)
Actual labor cost (to date)
Actual labor cost/MHr (to date) | Actual labor cost per man hour (to date) |  | [Actual labor cost (to date)] ÷ [Actual MHrs (to date)]
Actual labor unit cost (to date) |  |  | [Actual labor cost (to date)] ÷ [Actual qty (to date)]
Actual materials cost (to date)
Actual MHrs (to date) | Actual man hours claimed (to date) | IF Estimated actual MHrs is ON, THEN [Confirmed actual MHrs] + [Estimated actual MHrs]
Actual MHrs/unit (to date) | Actual man hours per unit (to date) |  | [Actual MHrs (to date)] ÷ [Actual qty (to date)]
Actual qty (to date) | Actual quantity claimed (to date) | IF Estimated actuals is ON, THEN [Confirmed actual qty] + [Estimated actual qty]
Actual start
Actual subcontract cost (to date)
Actual supplies cost (to date)
Actual undefined cost (to date)
Actual unit cost (to date) | Actual unit cost (to date) |  | [Actual cost (to date)] ÷ [Actual qty (to date)]
Actual units/MHr (to date) | Actual units per man hour (to date) |  | [Actual qty (to date)] ÷ [Actual MHrs (to date)]
Actual vendor MHrs (to date) | Actual vendor man hours claimed (to date)
Allow as-built |  | Sets the type of actuals able to be associated to the cost item.
Approved budget changes |  |  | [CB Total Cost] - [OB Total Cost]
As-built lock |  | The cost item can't receive claimed actuals when checked.
Assigned vendor |  | Associated vendor to the Contracts containing this cost item or manually selected.
Average performance setting |  | An way to specify a date range to consider the actuals for when Average performance forecast method is selected for the cost item.
Baseline actual finish
Baseline actual start
Baseline early finish
Baseline early start
Baseline finish
Baseline late finish
Baseline late start
Baseline plug days
Baseline roll up schedule
Baseline schedule ID |  | Used to map to the representative line item in the baseline schedule for integrations.
Baseline schedule plug days
Baseline schedule WBS | Baseline schedule work breakdown structure
Baseline scheduled |  | Used to determine if schedule information is integrated
Baseline start
Budget lock status |  | Indicator that represents if the current and original budget values are locked or not
Budget segment 1
Budget segment 2
Budget segment 3
Budget segment 4
CB actual cost G/L (to date) | Current budget actual cost gain/loss (to date) |  | [CB cost earned] - [Actual cost (to date)]
CB allowance total cost | Current budget cotingency (allowances) total cost
CB construction equipment total cost | Current budget construction equipment total cost
CB cost burn rate | Current budget cost burn rate |  | [Actual cost (to date)] ÷ [CB cost earned]
CB cost earned | Current budget cost earned |  | [% complete] × [CB total cost]
CB cost expended % | Current budget cost expended percent |  | [Actual cost (to date)] ÷ [CB total cost]
CB CPI | Current budget construction performance indicator |  | [CB cost earned] ÷ [Actual cost (to date)]
CB earned qty | Current budget earned quantity |  | [% complete] × [CB total qty]
CB earned unit cost | Current budget earned unit cost |  | [CB cost earned] ÷ [Actual qty (to date)]
CB fees total cost | Current budget fixed fees and services total cost
CB FOM rented equipment total cost | Current budget field operated and maintained rented equipment total cost
CB forecast G/L | Current budget forecast gain/loss |  | [CB total cost] - [Forecast total cost]
CB forecast G/L % | Current budget forecast gain/loss percent |  | [CB forecast G/L] ÷ [CB total cost]
CB forecast total MHr G/L | Current budget forecast total man hour gain/loss |  | [CB total MHrs] - [Forecast total MHrs]
CB forecast total MHr G/L % | Current budget forecast total man hour gain/loss percent |  | [CB forecast total MHr G/L] ÷ [CB total MHrs]
CB forecast unit cost G/L | Current budget forecast unit cost gain/loss |  | [CB unit cost] - [Forecast total unit cost]
CB forecast unit cost G/L % | Current budget forecast unit cost gain/loss percent |  | [CB forecast unit cost G/L] ÷ [CB earned unit cost]
CB G & A total cost | Current budget general and administrative expense total cost
CB labor total cost | Current budget labor total cost
CB labor unit cost | Current budget labor unit cost |  | [CB labor total cost] ÷ [CB total qty]
CB man hour burn rate | Current budget man hour burn rate |  | [Actual MHrs (to date)] ÷ [CB MHrs earned]
CB materials total cost | Current budget materials total cost
CB MHrs earned | Current budget man hours earned |  | [% complete] × [CB total MHrs]
CB MHrs expended % | Current budget man hours expended percent |  | [Actual MHrs (to date)] ÷ [CB total MHrs]
CB MHrs G/L % (to date) | Current budget man hours gain/loss percent |  | [CB MHrs G/L (to date)] ÷ [CB MHrs earned]
CB MHrs G/L (to date) | Current budget man hours gain/loss (to date) |  | [CB MHrs earned] - [Actual MHrs (to date)]
CB MHrs/unit | Current budget man hours per unit |  | [CB total MHrs] ÷ [CB total qty]
CB planned % complete | Current budget planned % complete |  | [CB planned value (to date)/[CB total cost]
CB planned value (to date) | Current budget schedule planned value (to date) |  | IF Time phased budget is being used Then CB planned value = mx + b WHERE m = Current Fiscal Time phased budget cost / (Current fiscal month end date - Current fiscal period month start date) b = sum(Time phased budget cost in the past fiscal periods x = today's date - current fiscal period month start date ELSE IF Time phased budget is not being used Then CB planned value = Value % (additive) * CB total Cost WHERE Value % (additive) = mx + B m = Slope of the cost curve segment x = Total duration % - To duration % b = Value % (additive) of the cost curve segment
CB productivity factor | Current budget productivity factor |  | [CB MHrs earned] ÷ [Actual MHrs (to date)]
CB remaining cost | Current budget remaining cost |  | [CB total cost] - [CB cost earned]
CB remaining cost % | Current budget remaining cost percent |  | [CB remaining cost] ÷ [CB total cost]
CB remaining MHrs | Current budget remaining man hours |  | [CB total MHrs] - [CB MHrs earned]
CB remaining qty | Current budget remaining quantity |  | [CB total qty] - [CB earned qty]
CB subcontract total cost | Current budget subcontract total cost
CB supplies total cost | Current budget supplies total cost
CB total cost | Current budget total cost
CB total cost G/L % | Current budget total cost gain/loss percent |  | [CB actual cost G/L (to date)] ÷ [CB cost earned]
CB total labor cost/MHr | Current budget total labor cost per man hour |  | [CB labor total cost] ÷ [CB total MHrs]
CB total MHrs | Current budget total man hours
CB total quantity | Current budget total quantity
CB undefined total cost | Current budget undefined total cost
CB unit cost | Current budget unit cost |  | [CB total cost] ÷ [CB total qty]
CB unit cost G/L | Current budget unit cost gain/loss |  | [CB earned unit cost] - [Actual unit cost (to date)]
CB unit cost G/L % | Current budget unit cost gain/loss percent |  | [CB unit cost G/L] ÷ [CB earned unit cost]
CB units/Mhr | Current budget units per man hour |  | [CB total qty] ÷ [CB total MHrs]
CBS contribute qty | Cost breakdown structure contribute quantity | When checked and the UoM of this item matches the parent, the Forecast (T/O) qty adds with any other selected siblings to the parent.
CBS position | Cost breakdown structure position
CBS tag 1
CBS tag 10
CBS tag 11
CBS tag 12
CBS tag 13
CBS tag 14
CBS tag 15
CBS tag 16
CBS tag 17
CBS tag 18
CBS tag 19
CBS tag 2
CBS tag 20
CBS tag 21
CBS tag 22
CBS tag 23
CBS tag 24
CBS tag 25
CBS tag 3
CBS tag 4
CBS tag 5
CBS tag 6
CBS tag 7
CBS tag 8
CBS tag 9
CBS URL 1 | Cost breakdown structure uniform resource locator 1 | URL is configured in settings.
CBS URL 2 | Cost breakdown structure uniform resource locator 2 | URL is configured in settings.
CBS URL 3 | Cost breakdown structure uniform resource locator 3 | URL is configured in settings.
CBS URL 4 | Cost breakdown structure uniform resource locator 4 | URL is configured in settings.
CBS URL 5 | Cost breakdown structure uniform resource locator 5 | URL is configured in settings.
CBS URL 6 | Cost breakdown structure uniform resource locator 6 | URL is configured at the Organizational settings
CBS URL 7 | Cost breakdown structure uniform resource locator 7 | URL is configured at the Organizational settings
CBS URL 8 | Cost breakdown structure uniform resource locator 8 | URL is configured at the Organizational settings
CBS user defined 1
CBS user defined 10
CBS user defined 11
CBS user defined 12
CBS user defined 13
CBS user defined 14
CBS user defined 15
CBS user defined 2
CBS user defined 3
CBS user defined 4
CBS user defined 5
CBS user defined 6
CBS user defined 7
CBS user defined 8
CBS user defined 9
CE actual cost G/L % (to date) | Current estimate actual cost gain/loss percent (to date) |  | [CE actual cost G/L (to date)] ÷ [CE cost earned]
CE actual cost G/L (to date) | Current estimate actual cost gain/loss (to date) |  | [CE cost earned] - [Actual cost (to date)]
CE allowance total cost | Current estimate contingency (allowances) total cost
CE allowance unit cost | Current estimate contingency (allowances) unit cost |  | [CE allowance total cost] ÷ [Forecast (T/O) qty]
CE construction equipment total cost | Current estimate construction equipment total cost
CE construction equipment unit cost | Current estimate construction equipment unit cost |  | [CE construction equipment total cost] ÷ [Forecast (T/O) qty]
CE cost burn rate | Current estimate cost burn rate |  | [Actual cost (to date)] ÷ [CE cost earned]
CE cost earned | Current estimate cost earned |  | [% complete] × [CE total cost]
CE cost expended % | Current estimate cost expended percent |  | [CE cost earned] ÷ [CE total cost]
CE CPI | Current estimate construction performance index |  | [CE cost earned] ÷ [Actual cost (to date)]
CE eqp cost/hr | Current estimate equipment cost per hour
CE eqp hrs earned | Current estimate equipment hours earned |  | [Actual qty (to date)] ÷ [Forecast (T/O) qty or CB total qty]
CE eqp hrs expended % | Current estimate equipment hours expended percent |  | [Actual eqp hrs (to date)] ÷ [CE total eqp hrs]
CE eqp hrs/unit | Current estimate equipment hours per unit |  | [CE total eqp hrs] ÷ [Forecast (T/O) qty]
CE fees total cost | Current estimate fixed fees and services total cost
CE fees unit cost | Current estimate fixed fees and services unit cost |  | [CE fees total cost] ÷ [Forecast (T/O) qty]
CE FOM rented equipment total cost | Current estimate field operated and maintained rented equipment total cost
CE FOM rented equipment unit cost | Current estimate field operated and maintained rented equipment unit cost |  | [CE FOM rented equipment total cost] ÷ [Forecast (T/O) qty]
CE forecast cost G/L % | Current estimate forecast cost gain loss percent |  | [CE forecast total cost G/L] ÷ [CE total cost]
CE forecast MHr G/L | Current estimate forecast man hour gain/loss |  | [CE total MHrs] - [Forecast total MHrs]
CE forecast total cost G/L | Current estimate forecast total cost gain/loss |  | [CE total cost] - [Forecast total cost]
CE forecast unit cost G/L | Current estimate forecast total cost gain/loss |  | [Forecast total unit cost] - [CE unit cost]
CE forecast unit cost G/L % | Current estimate forecast unit cost gain/loss percent |  | [CE forecast unit cost G/L] ÷ [CE unit cost]
CE G & A total cost | Current estimate general and administrative expense total cost
CE G & A unit cost | Current estimate general and administrative expense unit cost |  | [CE G & A total cost] ÷ [Forecast (T/O) qty]
CE labor total cost | Current estimate labor total cost
CE labor unit cost | Current estimate labor unit cost |  | [CE labor total cost] ÷ [Forecast (T/O) qty]
CE materials total cost | Current estimate materials total cost
CE materials unit cost | Current estimate materials unit cost |  | [CE materials total cost] ÷ [Forecast (T/O) qty]
CE MHr burn rate | Current estimate man hour burn rate |  | [Actual MHrs (to date)] ÷ [CE MHrs earned]
CE MHr total G/L % | Current estimate man hours total gain/loss percent |  | [CE forecast MHr G/L] ÷ [CE total MHrs]
CE MHrs earned | Current estimate man hours earned |  | [% complete] × [CE total MHrs]
CE MHrs expended % | Current estimate man hours expended percent |  | [Actual MHrs (to date)] ÷ [CE total MHrs]
CE MHrs G/L % | Current estimate man hours gain/loss percent |  | [CE MHrs G/L (to date)] ÷ [CE MHrs earned]
CE MHrs G/L (to date) | Current estimate man hours gain/loss (to date) |  | [CE MHrs earned] - [Actual MHrs (to date)]
CE MHrs/unit | Current estimate man hours per unit |  | [CE total MHrs] ÷ [Forecast (T/O) qty]
CE productivity factor | Current estimate productivity factor |  | [CE MHrs earned] ÷ [Actual MHrs (to date)]
CE remaining cost | Current estimate remaining cost |  | [CE total cost] - [CE cost earned]
CE remaining cost % | Current estimate remaining cost percent |  | [CE remaining cost] ÷ [CE total cost]
CE remaining eqp hrs | Current estimate remaining equipment hours |  | [CE total eqp hrs] - [Actual eqp hrs (to date)]
CE remaining MHrs | Current estimate remaining man hours |  | [CE total MHrs] - [CE MHrs earned]
CE subcontract total cost | Current estimate subcontract total cost
CE subcontract unit cost | Current estimate subcontract unit cost |  | [CE subcontract total cost] ÷ [Forecast (T/O) qty]
CE supplies total cost | Current estimate supplies total cost
CE supplies unit cost | Current estimate supplies unit cost |  | [CE supplies total cost] ÷ [Forecast (T/O) qty]
CE total cost | Current estimate total cost
CE total eqp hrs | Current estimate total equipment hours
CE total labor cost/MHr | Current estimate total labor cost per man hour |  | [CE labor total cost] ÷ [CE total MHrs]
CE total MHrs | Current estimate total man hours
CE undefined total cost | Current estimate undefined total cost
CE undefined unit cost | Current estimate undefined unit cost |  | [CE undefined total cost] ÷ [Forecast (T/O) qty]
CE unit cost | Current estimate unit cost |  | [CE total cost] ÷ [Forecast (T/O) qty]
CE unit cost (to date) | Current estimate unit cost (to date) |  | [CE cost earned] ÷ [Actual qty (to date)]
CE unit cost G/L | Current estimate unit cost gain/loss |  | [CE unit cost (to date)] - [Actual unit cost (to date)]
CE unit cost G/L % | Current estimate unit cost gain/loss percent |  | [CE unit cost G/L] ÷ [CE unit cost]
CE units/eqp hr | Current estimate units per equipment hour |  | [Forecast (T/O) qty] ÷ [CE total eqp hrs]
CE units/MHr | Current estimate units per man hour |  | [Forecast (T/O) qty] ÷ [CE total MHrs]
Change status |  | Hover over an icon for more information on budget moves or contract adjustments.
Committed remaining cost |  | Remaining value of contractual obligations
Committed total cost |  | Total value of contractual obligations
Compensation factor (to date) |  |  | [CB labor unit cost] ÷ [Actual labor unit cost (to date)]
Confirmed actual cost |  | Verified expended cost
Confirmed actual equipment hours |  | Verified expended equipment hours
Confirmed actual man hours |  | Verified expendend man hours
Confirmed actual qty | Confirmed actual quantity | Verified completed work
Cost curve |  | Used for time phasing
Cost segment
Cost source |  | Determines which method of estimation is being utilized for current estimate values.
Currency
Data source
Delta from straight line |  | The difference between the Forecast total cost of the Live forecast and the average performance forecast method. | IF Forecast method <> Average performance THEN IF % complete >= "% Complete value at which delta from straight line calculation utilizes average performance" setting THEN = Forecast remaining cost - (Unit cost (to-date)*Qty remaining) ELSE THEN = Forecast total cost – CB total cost ELSE 0
Description
Design total Mhrs
Early finish
Early start
Engineer
Estimated actual cost |  | Estimated cost based on quantity claimed. Can reverse this value when confirmed cost is receieved.
Estimated actual equipment hours |  | Estimated equipment hours based on quantity claimed or hours claimed in Progress. Can reverse this value when confirmed hours are receieved.
Estimated actual man hours |  | Estimated man hours based on quantity claimed or hours claimed in Progress. Can reverse this value when confirmed hours are receieved.
Estimated actual qty | Estimated actual quantity | Preliminary claimed quantity from Plan application. Translates to confirmed quantity when sync'd from the actions menu.
Finish |  | Used for time phasing
Forecast % margin | Forecast percent margin |  | [Forecast total margin] ÷ [Forecast total revenue]
Forecast (T/O) qty | Forecast (take-off) quantity | Currently estimated and forecasted quantity at completion.
Forecast allowance total cost | Forecast contingency (allowances) total cost |  | [Forecast remaining allowance total cost] + [Actual allowance cost (to date)]
Forecast construction equipment total cost |  |  | [Forecast remaining construction equipment cost] + [Actual construction equipment cost (to date)]
Forecast cost change |  |  | [Current Forecast total cost] - [Previous month forecast total cost]
Forecast cost G/L change | Forecast cost gain/loss change |  | [Current CB forecast total cost G/L] - [Previous month CB forecast total cost G/L]
Forecast custom variable 1
Forecast custom variable 2
Forecast custom variable 3
Forecast fees total cost | Forecast fixed fees and services total cost |  | [Forecast remaining fees cost] + [Actual fees cost (to date)]
Forecast FOM rented equipment total cost | Forecast field operated and maintained equipment total cost |  | [Forecast remaining FOM rented equipment cost] + [Actual FOM rented equipment cost (to date)]
Forecast G & A total cost | Forecast general and administrative expense total cost |  | [Forecast remaining G & A cost] + [Actual G & A cost (to date)]
Forecast labor total cost |  |  | [Forecast remaining labor cost] + [Actual labor cost (to date)]
Forecast materials total cost |  |  | [Forecast remaining materials cost] + [Actual materials cost (to date)]
Forecast method |  | Determines which method of calculation is used for forecast.
Forecast MHrs earned | Forecast man hours earned |  | [Forecast total MHrs] × [% complete]
Forecast notes
Forecast remaining allowance total cost | Forecast remaining contingency (allowances) cost
Forecast remaining construction equipment cost
Forecast remaining cost |  |  | IF Forecast method = Current budget THEN = CB unit cost * Remaining qty ELSE IF Forecast method = Current estimate THEN = CE unit cost * Remaining qty ELSE IF Forecast method = Average performance THEN = Actual unit cost (to date) * Remaining qty ELSE IF Forecast method = Committed cost THEN = Committed remaining cost ELSE IF Forecast method = Contract THEN = Forecast total cost - Actual cost (to date) ELSE IF Forecast method = Manual (EAC) THEN = Forecast remaining unit cost * Remaining qty ELSE IF Forecast method = Manual (ETC) THEN = Forecast remaining unit cost * Remaining qty ELSE IF Forecast method = Detailed ETC THEN = sum(Resource Forecast remaining cost) for all assigned resources ELSE IF Forecast method = None THEN = 0 ELSE IF Forecast method = Rollup THEN = sum of direct children's Forecast remaining cost
Forecast remaining fees cost | Forecast remaining fixed fees and services cost
Forecast remaining FOM rented equipment cost | Forecast remaining field operated and maintained equipment cost
Forecast remaining G & A cost | Forecast remaining general and administrative expense cost
Forecast remaining labor cost
Forecast remaining labor cost/MHr | Forecast remaining labor cost per man hour |  | [Forecast remaining labor cost] ÷ [Forecast remaining MHrs]
Forecast remaining materials cost
Forecast remaining MHrs | Forecast remaining man hours |  | IF Forecast method = Current budget THEN = CB MHrs/unit * Remaining qty ELSE IF Forecast method = Current estimate THEN = CE MHrs/unit * Remaining qty ELSE IF Forecast method = Average performance THEN = Actual MHrs/unit (to date) * Remaining qty ELSE IF Forecast method = Committed cost THEN = 0 ELSE IF Forecast method = Contract THEN = 0 ELSE IF Forecast method = Manual (EAC) THEN = Forecast remaining labor cost/Forecast remaining labor cost/MHr ELSE IF Forecast method = Manual (ETC) THEN = Forecast Remaining mhrs/unit * Remaining quantity ELSE IF Forecast method = Detailed ETC THEN = sum for all resources assigned to the cost item IF resource is a labor resource Remaining qty * Remaining mhrs/unit ELSE 0 ELSE IF Forecast method = None THEN = 0 ELSE IF Forecast method = Rollup THEN = sum of direct children's Forecast remaining MHrs
Forecast remaining MHrs/unit | Forecast remaining man hours per unit |  | [Forecast remaining MHrs] ÷ [Remaining qty]
Forecast remaining productivity factor |  |  | [CB remaining MHrs] ÷ [Forecast remaining MHrs]
Forecast remaining revenue |  |  | [Forecast total revenue] - [Forecast revenue earned]
Forecast remaining subcontract cost
Forecast remaining supplies cost
Forecast remaining undefined cost
Forecast remaining unit cost |  |  | [Forecast remaining cost] ÷ [Remaining qty]
Forecast revenue earned |  | This depends on Earnings timing rules as well | [% complete] × [Forecast total revenue]
Forecast revenue unit cost |  |  | [Forecast total revenue] ÷ [Pay item Forecast (T/O) qty]
Forecast subcontract total cost |  |  | [Forecast remaining subcontract cost] + [Actual subcontract cost (to date)]
Forecast supplies total cost |  |  | [Forecast remaining supplies cost] + [Actual supplies cost (to date)]
Forecast (T/O) - CB qty delta |  |  | Forecast (T/O) qty - CB total qty
Forecast (T/O) - Component qty delta |  |  | Forecast (T/O) qty - Component qty
Forecast (T/O) - Design qty delta |  |  | Forecast (T/O) qty - Design qty
Forecast total cost |  |  | [Actual cost (to date)] + [Forecast remaining cost]
Forecast total labor cost/MHr | Forecast total labor cost per man hour |  | [Forecast labor total cost] ÷ [Forecast total MHrs]
Forecast total margin |  |  | [Forecast total revenue] - [Forecast total cost]
Forecast total MHrs | Forecast total man hours |  | [Forecast remaining MHrs] + [Actual MHrs (to date)]
Forecast total MHrs/unit | Forecast total man hours per unit |  | [Forecast total MHrs] ÷ [Forecast (T/O) qty]
Forecast total productivity factor |  |  | [CB total MHrs] ÷ [Forecast total MHrs]
Forecast total revenue |  |  | IF Pay item assignment <> blank THEN IF Assigned pay item has Billing method = Cost plus THEN IF Pay item revenue forecast method = Earned THEN IF Cost source = Plug THEN CE revenue amount ELSE THEN Forecast total revenue (labor resource) + Forecast total revenue (construction equipment resource) + Forecast total revenue (all other resources) ELSE IF Pay item revenue forecast method = Billed THEN IF all of the Billed revenue is assigned to cost item(s) THEN Forecast remaining revenue + Billed revenue assigned to the cost item ELSE THEN Forecast remaining revenue + (Billed Revenue of the pay item unassigned to a cost item * (CE total cost of the cost item/CE total cost of all cost items assigned to the pay item) + Billed Revenue assigned to the cost item) ELSE IF Pay item revenue forecast method = Manual THEN Pay item Forecast total revenue * (CE total cost of the cost item/CE total cost of all cost items assigned to the pay item) ELSE IF Assigned pay item has billing method = Fixed final price OR Unit price THEN Pay item forecast total revenue * Earning % ELSE 0
Forecast total unit cost |  |  | [Forecast total cost] ÷ [Forecast (T/O) qty]
Forecast undefined total cost |  |  | [Forecast remaining undefined cost] + [Actual undefined cost (to date)]
Has as-built entries |  | Indicator that represents if actuals have been claimed against that cost item or not
Hide in Plan, and Progress and Design |  | The cost item can't be claimed against in Plan, Progress or Design when checked.
Improvement factor |  |  | [Actual unit cost (to date)] ÷ [Forecast remaining unit cost]
Is terminal
Issue |  | Can select an issue number from Change
Issue cost |  | Cost item that has cost associated to an issue in Change but is not a PCO or CCO
Last estimated actual cost reversal |  | Date and time estimated cost was negated to zero
Last estimated actual eqp hours reversal | Last estimated actual equipment hours reversal | Date and time esimated equipment hours were negated to zero
Last estimated actual man hours reversal |  | Date and time estimated man hours were negated to zero
Late finish
Late start
LEI (to date) | Labor efficiency index (to date) |  | [CB productivity factor] × [Compensation factor (to date)]
Notes
Number of contracts |  | Number of associated contracts in the Contract application
OB allowance total cost | Original budget contingency (allowances) total cost
OB construction equipment total cost | Original budget construction equipment total cost
OB fees total cost | Original budget fixed fees and services total cost
OB FOM rented equipment total cost | Original budget field operated and maintained rented equipment total cost
OB G & A total cost | Original budget general and administrative expense total cost
OB labor total cost | Original budget labor total cost
OB materials total cost | Original budget materials total cost
OB subcontract total cost | Original budget subcontract total cost
OB supplies total cost | Original budget supplies total cost
OB total cost | Original budget total cost
OB total MHrs | Original budget total man hours
OB total qty | Original budget total quantity
OB undefined total cost | Original budget undefined total cost
OB unit cost | Original budget unit cost |  | [OB total cost] ÷ [OB total qty]
OB UoM | Original budget unit of measure
Optional code
Pay item assignment
Pending budget cost |  | Pending budget move or contract adjustment value awaiting approval
Phased forecast remaining cost delta |  |  | [Total sum of remaining cost in open phased forecast cells] - [Forecast remaining cost]
Phased forecast remaining MHrs delta | Phased forecast remaining man hours delta |  | [Total sum of remaining MHrs in open phased forecast cells] - [Forecast remaining MHrs]
Phased forecast remaining qty delta | Phased forecast remaining quantity delta |  | [Total sum of remaining qty in open phased forecast cells] - [Remaining qty]
Plan component total qty
Plug days
Progress actual start date
Qty driver | Quantity driver | Superior cost item: When the parent Forecast (T/O) qty is updated, this item will update by the same ratio of change. Fixed: Forecast (T/O) qty will not update when the parent qty is changed.
Remaining qty | Remaining quantity |  | [Forecast (T/O) qty] - [Actual qty (to date)]
Resources |  | Number of estimate resources employed to the cost item
Rework |  | Indicates if the cost item was rework or not
Roll up schedule
Scale 1 |  | When using estimating resources to produce current estimate values, this is the percent of labor time charged at Scale 1 unit rates.
Scale 2 |  | When using estimating resources to produce current estimate values, this is the percent of labor time charged at Scale 2 unit rates.
Scale 3 |  | When using estimating resources to produce current estimate values, this is the percent of labor time charged at Scale 3 unit rates.
Schedule ID |  | Used to map to the representative line item in the schedule for integrations.
Schedule plug days
Schedule WBS | Schedule work breakdown structure
Scheduled |  | Used to determine if schedule information is integrated
Secondary qty | Secondary quantity
Secondary UoM | Secondary unit of measure | Secondary measurement unit that represents the cost item. Pairs with Secondary qty.
SPI | Schedule performance index |  | [CB cost earned] / [CB planned value (to date)]
Start |  | Used for time phasing
UoM | Unit of measure | Primary measurement unit that represents the cost item. Pairs with all quantities except original budget quantity and secondary quantity.
WBS phase code | Work breakdown structure phase code

## Change Log (hidden)
Name | Date | Tab | IS Column Name | Field Changed | Value Before | Value After | Notes
Morgan | 2016-12-06 |  | C B-MH Earned (To Date) | Rollup Rules | [blank] | Sum of children one level below
Morgan | 2016-12-06 |  | C E-Eqp Hours Earned | Rollup Rules | [blank] | Sum of children one level below
Morgan | 2016-12-06 |  | C E-MH Earned (To Date) | Rollup Rules | [blank] | Sum of children one level below
Morgan | 2016-12-06 |  | C E-Cost Earned (To Date) | Rollup Rules | [blank] | Sum of children one level below
Morgan | 2016-12-18 | Estimate Resource Library |  | Tabs |  |  | Added this sheet to the workbook
Morgan | 2016-12-18 | Cost Item Details - Resources |  | Tabs |  |  | Added this sheet to the workbook
Bridgette | 2017-01-03 | [5 empty] | Uploaded latest version to confluence
Bridgette | 2017-01-17 | CBS Data Block Master | C B-Forecast Final MH G/L % | added % | C B-Forecast Final MH G/L | C B-Forecast Final MH G/L %
Bridgette | 2017-01-17 | CBS Data Block Master | C B-MH G/L % (To Date) | added % | C B-MH G/L (To Date) | C B-MH G/L % (To Date)
Morgan | 2017-01-19 | Cost Item Details - Resources | ALL | [Mapping] Column from Estimate Resource Library | null | added column | added a column to map the column from the estimate resource library to the cost item details slideout
Morgan | 2017-01-19 | Estimate Resource Library | ALL | IS Column Name | null | added column | added a column for the intended IS column name
Bridgette | 2017-01-20 | Estimate Resource Library |  | Added Column "Visible in Rate Record Setup section" | null | Added designation of rows to be visible in order of operation
Morgan | 2017-01-23 | Resource Calculations | ALL! |  | null | added tab
Morgan | 2017-03-09 | CBS Data Block Master | Data Type (Validation) | Added | null | Added column | Added column for purposes of Paste user story
Emmanuel | 2017-04-13 | CBS Data Block Master | C E-FOM Rented Eqp-Unit Cost | IS Column Name | Descr: Fully Operated and Maintained Rented Equipment Total Cost Formula: C E-FOM Rented Equipment Total Cost / Forecast (T/O) Qty | Descr: Fully Operated and Maintained Rented Equipment Unit Cost Formula: C E-FOM Rented Equipment Total Cost / Forecast (T/O) Qty | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | C E-G & A Unit Cost | Tool Tip (New) | Descr: Current Budget General And Administrative Expense Unit Cost Formula: C E-G & A Total Cost / Forecast (T/O) Qty | Descr: Current Estimate General And Administrative Expense Unit Cost Formula: C E-G & A Total Cost / Forecast (T/O) Qty | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | C B-Earned Unit Cost | Dependent 1 | C B-Total Cost | C B-Earned Total Cost (To Date) | Changed to correct equation
Emmanuel | 2017-04-13 | CBS Data Block Master | C B-Earned Unit Cost | Dependent 2 | Forecast (T/O) Qty | Qty Complete (To Date) | Changed to correct equation
Emmanuel | 2017-04-13 | CBS Data Block Master | C B-Earned Qty | Tool Tip (New) | Descr: Current Budget Earned Man Hours Formula: % Complete * C B-Total Quantity | Descr: Current Budget Earned Quantity Formula: % Complete * C B-Total Quantity | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | Plan Qty | Tool Tip (New) | Descr: Sum of Plan component quantities Formula: N/A | Descr: Sum of Plan component quantities Formula: N/A | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | Forecast Remaining Construction Equipment Cost | Tool Tip (New) | Descr: Forecast Remaining Construction Equipment Cost Formula: N/A | Descr: Forecast Remaining Construction Equipment Cost Formula: N/A | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | Forecast Remaining F O M Rented Equipment Cost | Tool Tip (New) | Descr: Forecast Remaining Fully Operated and Maintained Rented Equipment Cost Formula: N/A | Descr: Forecast Remaining Fully Operated and Maintained Rented Equipment Cost Formula: N/A | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | Forecast Remaining Supplies Cost | Tool Tip (New) | Descr: Forecast Remaining Supplies Cost Formula: N/A | Descr: Forecast Remaining Supplies Cost Formula: N/A | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | Forecast Remaining Materials Cost | Tool Tip (New) | Descr: Forecast Remaining Materials Cost Formula: N/A | Descr: Forecast Remaining Materials Cost Formula: N/A | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | Forecast Remaining Subcontract Cost | Tool Tip (New) | Descr: Forecast Remaining Subcontract Cost Formula: N/A | Descr: Forecast Remaining Subcontract Cost Formula: N/A | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | Forecast Remaining Fixed Fees and Services Cost | Tool Tip (New) | Descr: Forecast Remaining Fixed Fees and Services Cost Formula: N/A | Descr: Forecast Remaining Fixed Fees and Services Cost Formula: N/A | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | Forecast Remaining Contingency ( Allowances) Cost | Tool Tip (New) | Descr: Forecast Remaining Contingency ( Allowances) Cost Formula: N/A | Descr: Forecast Remaining Contingency ( Allowances) Cost Formula: N/A | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | Forecast Remaining G & A Cost | Tool Tip (New) | Descr: Forecast Remaining General And Administrative Cost Formula: N/A | Descr: Forecast Remaining General And Administrative Cost Formula: N/A | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-13 | CBS Data Block Master | Forecast Remaining Undefined Cost | Tool Tip (New) | Descr: Forecast Remaining Undefined Cost Formula: N/A | Descr: Forecast Remaining Undefined Cost Formula: N/A | Updated tool tips to correct description (US 213846)
Emmanuel | 2017-04-19 | CBS Data Block Master | Multiple | Multiple |  |  | Strke through on all the ACS values in the 'CBS Data Block Master' tab
Emmanuel | 2017-04-19 | ACS | Multiple | Release |  |  | Updated release to R3 on the User Defined Fields and tags 6-20
Emmanuel | 2017-05-11 | CBS Data Block Master | C E-Forecast Unit Cost G/L | Dependencies |  |  | corrected the equation. Was swapped around before
Emmanuel | 2017-08-02 | CBS Data Block Master | Multiple | Unlock? Column Created |  |  | Created the column for US
Emmanuel | 2017-08-18 | CBS Data Block Master | Multiple | Column: AH - Clear Data on Budget Unlock |  |  | Created the column for US
Emmanuel | 2017-08-18 | CBS Data Block Master | Multiple | Column: AI - On Budget Lock - Copy Value from: |  |  | Created the column for US
Emmanuel | 2017-08-25 | CBS Data Block Master | Multiple | Column: AJ - Excel Import - Map Column |  |  | Created the column for US
Ashima | 2017-09-19 | Estimate Resource Library | Maint. Man-Hours | Data type | subtotal | Number | =
Emmanuel | 2017-09-27 | CBS Data Block Master | Validation failure error message/tool tip | All | None | Validation
Emmanuel | 2017-09-27 | CBS Data Block Master | Validation for Excel Import | All | None | Validation
Ashima | 2017-12-18 | CBS Data Block Master | Estimate Import - Map Column | All | None | Map | Create for estimate import - mapping page.

## Column Headers (template) (hidden)
Order in the Data Block
Column Chooser Category
Permissions Level | Order in the Data Block | Column Chooser Category | Permissions Level | Kiewit Custom HD Column Name | HD Default Column Name | IS Column Name | Dependent 1 | Mathematical Operator | Dependent 2 | Rollup Rules | Tool Tip | Column Detailed Description | Formula | Release | Editable in Workspace | User Story | Note
Kiewit Custom HD Column Name
HD Default Column Name
IS Column Name
Dependent 1
Mathematical Operator
Dependent 2
Rollup Rules
Tool Tip
Column Detailed Description
Formula
Release
Editable in Workspace
User Story
Note
Pulls From Library data? (reference where in this cell)
Expected Data Type
Type of validation required